## Sheet1
Project Name | Note Taking Website | [6 empty] | Overdue
Project Manager | Kimberly H.
Project Deliverable | Soham A.
Start Date | 2023-02-06
End Date | 2023-05-08
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11
2023-03-19
Deliverable 2 |  | 2023-03-05 | 2023-03-19 | 14 | Complete
Agree on objectives |  | 2023-03-10 | 2023-03-19 | 9 | Complete
Initiation
Detailed Reqs. | Kristen J. | 2023-03-05 | 2023-03-09 | 4 | Complete
Hardware Reqs. | Wentao C. | 2023-03-05 | 2023-03-10 | 5 | Complete
Final Resource Plan | Soham A. | 2023-03-05 | 2023-03-07 | 2 | Complete
Staffing | Kimberly H. | 2023-03-05 | 2023-03-06 | 1 | Complete
Development
Technical Reqs. | Paul R. | 2023-03-05 | - | - | In progress
DB Development | Wentao C. | 2023-03-05 | - | - | In progress
API Development | Soham A. | 2023-03-05 | - | - | In progress
UI Client | Catherine V. | - | - | - | Not started
Testing | Kristen J. | - | - | - | Not started
Dev. Complete | Kimberly H. | - | - | - | Not started
Operations
Hardware Config. | Wentao C. / Soham A. | - | - | - | Not started
System Testing | Kimberly H. / Kristen J. | - | - | - | Not started
Launch